## Trang tính1
90 |  | Java Fresher Project Tasks
No. | Task | Assignee | Duration(Day/Hour) | Start Day | Finish Day | Predecessors | Team | Completed (%)
1 | Discuss about requirement of the project | All members | 2 hours | 2017-10-04 | 2017-10-04 |  | 1 | 100
2 | Research Sikuli | All members | 2 hours | 2017-10-04 | 2017-10-04 |  | 1 | 100
3 | How to use and sikuli's uses | Duc, Thien, Phuc | 4 hours | 2017-10-04 | 2017-10-04 |  | 1 | 100
4 | how to apply sikuli with eclipse | Bao, Thien, Thuyet | 3 hours | 2017-10-05 | 2017-10-05 |  | 1 | 100
5 | Build a app to demonstrate the sikuli's feature | Phuc | 3.5 hours | 2017-10-05 | 2017-10-05 |  | 1 | 100
6 | Research OSGI & it's uses | All members | 3 days | 2017-10-05 | 2017-10-09 |  | 1 | 100
7 | Knowing about OSGI's uses & how it works | Bao,Phuc,Thuyet | 3 days | 2017-10-06 | 2017-10-10 |  | 1 | 100
8 | Install bundle sikuli into OSGI | Phuc,Thien,Bao | 2 days | 2017-10-10 | 2017-10-11 |  | 1 | 100
9 | Create OSGI's service | All members | 3 days | 2017-10-13 | 2017-10-15 |  | 1 | 100
10 | Transfer data & method in OSGI | Duc,Thien,Bao | 3 days | 2017-10-14 | 2017-10-16 |  | 1 | 100
11 | Making a demonstrate in local computer | Phuc,Thuyet | 2 days | 2017-10-15 | 2017-10-16 |  | 1 | 100
12 | Integrate sikuli into OSGi project | Bao, Phuc, Duc | 2 day | 2017-10-17 | 2017-10-18 |  | 1 | 100
13 | Config OSGi server | Bao,Thuyet | 3 days | 2017-10-17 | 2017-10-19 |  | 1 | 100
14 | Config OSGi client | Phuc, Duc | 2 days | 2017-10-18 | 2017-10-19 |  | 1 | 100
15 | Making OSGI project and transfer via internet | All Members | 2 days | 2017-10-19 | 2017-10-20 |  | 1 | 100
16 | Merge Code's team-members | All members | 0.5 day | 2017-10-21 | 2017-10-21 |  | 1 | 100
1 | Discuss about work flow | All members | 0.5 day | 2017-10-03 | 2017-10-03 |  | 2 | 100
2 | Research projects API from SonarQube | Cuong | 3 hours | 2017-10-05 | 2017-10-05 |  | 2 | 100
3 | Discuss how to evaluate percent code coverage | All members | 1.5 hours | 2017-10-05 | 2017-10-05 |  | 2 | 100
4 | Discuss how to calculate number of Test case | All members | 1.5 hours | 2017-10-05 | 2017-10-05 |  | 2 | 100
5 | Discuss how to calculate number of Code smell | All members | 1.5 hours | 2017-10-06 | 2017-10-06 |  | 2 | 100
6 | Discuss how to calculate techniqual debt time | All members | 1.5 hours | 2017-10-06 | 2017-10-06 |  | 2 | 100
7 | Prepare Spring MVC configuration for project | Quang | 3 hours | 2017-10-07 | 2017-10-07 |  | 2 | 100
8 | Design simple HTML & CSS page | Trieu | 1.5 hours | 2017-10-08 | 2017-10-08 |  | 2 | 100
9 | Add Boostrap to front-end | Trieu | 1.5 hours | 2017-10-08 | 2017-10-08 |  | 2 | 100
10 | Write simple java method to get API from SonarQube | Cuong | 3 hours | 2017-10-08 | 2017-10-08 |  | 2 | 100
11 | Discuss about work flow and requirement one again | All members | 1.5 hours | 2017-10-09 | 2017-10-09 |  | 2 | 100
12 | Correct front-end page to match to requirement | Trieu | 1.5 hours | 2017-10-09 | 2017-10-09 |  | 2 | 100
13 | Design Database & Model for project | Cuong | 1 hour | 2017-10-09 | 2017-10-09 |  | 2 | 100
14 | Create database table with SQL | Quang | 0.5 hour | 2017-10-09 | 2017-10-09 |  | 2 | 100
15 | Prepare SQL query to retrive data from SonarQube | Dat | 3 hours | 2017-10-10 | 2017-10-10 |  | 2 | 100
16 | Prepare SQL query to update data from SonarQube | Dat | 1.5 hours | 2017-10-10 | 2017-10-10 |  | 2 | 100
17 | Build simple Spring MVC app and connect with database | Quang | 3 hours | 2017-10-10 | 2017-10-10 |  | 2 | 100
18 | Build Spring MVC App to get the SonarQube API Link | Quang, Trieu | 0.5 day | 2017-10-11 | 2017-10-11 |  | 2 | 100
19 | Build Spring MVC App to get the SonarQube API List Project and Modules | Quang | 0.5 day | 2017-10-11 | 2017-10-11 |  | 2 | 100
20 | Research library for chart | Cuong | 0.5 day | 2017-10-12 | 2017-10-12 |  | 2 | 100
21 | Build Simple Metrics Chart | Cuong | 0.5 day | 2017-10-12 | 2017-10-13 |  | 2 | 100
22 | Add Boostrap to Charts | Dat | 0.5 day | 2017-10-13 | 2017-10-13 |  | 2 | 100
23 | Edit Index Page with Daily Report Chart | Cuong , Dat | 0.5 day | 2017-10-13 | 2017-10-14 |  | 2 | 100
24 | Edit Index Page with Metrics Chart | Cuong , Dat | 0.5 day | 2017-10-14 | 2017-10-14 |  | 2 | 100
25 | Build simple table to show daily report in HTML & CSS | Cuong | 0.5 day | 2017-10-14 | 2017-10-14 |  | 2 | 100
26 | Add Angular code to daily report table | Cuong | 0.5 day | 2017-10-15 | 2017-10-15 |  | 2 | 100
27 | Complete Angular controller for daily report | Cuong | 0.5 day | 2017-10-15 | 2017-10-15 |  | 2 | 100
28 | Use Angular to get json data from RESTfull Webservice | Cuong | 0.5 day | 2017-10-16 | 2017-10-16 |  | 2 | 100
29 | Test Daily report with Angular after getted data from backend server | Cuong | 0.5 day | 2017-10-16 | 2017-10-16 |  | 2 | 100
30 | Draw Chart with Angular after getted data from backend server | Cuong | 0.5 day | 2017-10-17 | 2017-10-17 |  | 2 | 100
31 | Add routing to Angular application | Cuong | 0.5 day | 2017-10-18 | 2017-10-18 |  | 2 | 100
32 | Test & Demo Angular application | Cuong | 0.5 day | 2017-10-18 | 2017-10-18 |  | 2 | 100
33 | Correct the hibernate code | Quang, Trieu | 1 day | 2017-10-18 | 2017-10-19 |  | 2 | 100
34 | Change the hardcode to file properties | Trieu | 0.5 day | 2017-10-19 | 2017-10-19 |  | 2 | 100
35 | Build the update SonarQube feature with Http POST method in Spring MVC | Trieu | 0..5 day | 2017-10-19 | 2017-10-19 |  | 2 | 100
36 | Change the css type of front-end | Trieu,Dat | 1 h | 2017-10-19 | 2017-10-19 |  | 2 | 100
37 | Add filter technical debt feature using Angular | Cuong | 2h | 2017-10-19 | 2017-10-19 |  | 2 | 100
38 | Build the update SonarQube feature with Http POST method in front-end using Angular | Cuong | 2h | 2017-10-19 | 2017-10-19 |  | 2 | 100
39 | Change config XML in Hibernate for using MySQL | Quang | 2h | 2017-10-19 | 2017-10-19 |  | 2 | 100
40 | Add config XML in Hibernate for using SQL server | Quang | 2h | 2017-10-19 | 2017-10-19 |  | 2 | 100
45 | Review Code | All Members | 2h | 2017-10-20 | 2017-10-20 |  | 2 | 100
46 | Build Project into file war and setup on Trainer PC | Cuong , Trieu | 2h | 2017-10-20 | 2017-10-20 |  | 2 | 100
47 | Prepare slide for presentation | Dat, Cuong | 0.5 day | 2017-10-21 | 2017-10-21 |  | 2 | 100